## Sheet1
Week 1 | Review |  | Goals for creating bylaws and constitution.
Week 2 | Fill out empty constituion | I suggest we also write in specific sections we want to fill out. | One goal for creating the constitution/bylaws is so that our organization has a structure, and we can refer to the documents to establish a productive environment (e.g., bylaws, officer position, code of conduct).
Week 3 | Improve light berry red text/proof read |  | Another goal is to have a system in place to discourage inappropriate behavior (e.g., code of conduct).
Week 4 | Finalize constitution
Week 5 | Fill bylaws according to constitution powers
Week 6 | Discuss officer duties
Week 7 | Bylaws
Week 8 | Bylaws
Week 9 | Bylaws
Week 10 | Bylaws
Week 11 | Create code of conduct
Week 12 | Code of Conduct
Week 13 | Code of Conduct
Week 14 | Code of Conduct
Week 15 | Code of Conduct

## Constitution
Rank | Article | Section | Subsection | Task | Progress | 1st edit | Complete by | 2nd edit | complete by
Preamble
| I | none | none | none | complete
| II | none | none | none | complete
| III | I | none | Define powers of Bylaws
| III | II | none
1 | IV | I | 2018-01-04 |  | drafted | Caleb | Tues, Feb 22
1 | IV | II | 2018-01-06 | 3.4 needs completion | drafted | Rudy | Tues, Feb 22
1 | IV | III | 2018-01-02 |  |  | Aaron | Tues, Feb 22
2 | V | I | 2018-01-05 | Write draft of all subsections | complete | Caleb | Tues, Jan 30
2 | V | II | 2018-01-11 | Determine what goes in the bylaws |  | Aaron | 2018-02-07 | Aaron | Tues, Feb 22
3 | VI | I | none | Write first draft. |  | Rudy | Tues, Jan 23
3 | VI | II | 1
hi caleb

## Checklist
1 | First, we outline all the sections.
2 | Then, we assign small, manageable sections to a development members.
3 | Each week, the assigned member will draft a subsection no later than 2 days before the next meeting.
4 | Before the meeting, all development members will review and then create a list of feedback to discuss during the meeting.
5 | During the meeting, a different member will read aloud the drafted subsection and then all member will interrupt, as necessary, to discuss feedback.
6 | All major changes must be voted on by a majority vote.
7 | Immediately after the meeting ends, the responsibility for drafting the current or next subsection falls on the next member on the schedule. For example, if Person A worked on subsection 1, then Person B will work on subsection 1 or subsection for the next week.
8 | Follow steps 1 through 6 for the next person.